Гуманитарный проект

ГУДО «Центр творчества детей и молодежи Борисовского района»

Цель проекта: Оказание психо-социальной поддержки 10 семьям, на попечение которых находятся10 молодых инвалидов

| а. | Название проекта: | «Импульс» |
| --- | --- | --- |
| b. | Название первичной организации/клуба/волонтерской группы, подающей заявку: | ГУДО «Центр творчества детей и молодежи Борисовского района» |
| с. | Ф.И.О. руководителя первичной организации /клуба/ волонтерской группы: | Вербицкая Ольга Ивановна |
| d. | Контактный телефон: | +375298712080 |
| е. | Название предприятия, организации, учреждения, на базе которого будет реализоваться проект: которого | ГУДО «Центр творчества детей и молодежи Борисовского района» |
| f. | Место реализации (адрес по которому будет осуществляться проект) | Минская область, г. Борисов, ул. 8 Марта д. 26. Детская комната «УНИКУМ» ГУДО ЦТДиМ |
| g. | Ф.И.О. руководителя предприятия: | Лужковская Галина Александровна |
| h. | Номер телефона: | 8017(77)47072 |
| i. | Номер факса: | 8-017(77) 51789 |
| j. | Электронная почта: | ddut@tut.by |
| k. | Почтовый адрес: | 2222120 Минская обл., г. Борисов, ул. Дзержинского д. 42 |
| l. | Размер запрашиваемой финансовой поддержки: | 10 000 эквивалент в долларах США |

- Кто будет осуществлять проект? Укажите количество волонтеров, их возраст, место работы, должность. Укажите, кто является руководителем группы волонтеров и несет общую ответственность за осуществление проекта и отчетность. Вербицкая Ольга Ивановна - руководитель проекта – 36 лет, педагог дополнительного образования ГУДО «Центр творчества детей и молодежи Борисовского района». Волонтеры в количестве 6 чел. – учащиеся объединения по интересам «Леди совершенство» ГУДО «Центр творчества детей и молодежи Борисовского района» в возрасте 13-17 лет.

- Целевая группа проекта. Укажите, на какую целевую группу (возраст, число, вид занятости) будут направлены мероприятия. Десять семей, на попечение который находятся десять инвалидов в возрасте от 18 до 35 лет с нарушением опорно-двигательного аппарата. 3 инвалида проживают в неполных семьях, 6 волонтеров принимают участие в реализации проекта.

- Описание проекта 3.1. Описание проблемы/ситуации. В учреждении образования ГУДО «Центр творчества детей и молодежи Борисовского района» зачислено 4817 учащихся. Из них инвалидов 67. Десять семей, на попечении которых находятся 10 инвалидов в возрасте от 18 до 35 лет (ДЦП) готовы к приобретению профессиональных навыков в сфере бьюти индустрии (парикмахерское искусство, дизайнер одежды, демонстратор одежды) для дальнейшего самообеспечения и саморазвития.

3.2. Цель проекта Опишите, на достижение какой цели направлен проект. Цель–оказание психо-социальной поддержки семьям, на попечении которых находятся инвалиды.

3.3. Результаты проекта Опишите, конечный результат осуществления запланированных мероприятий, который можно будет увидеть и оценить (результатов может быть несколько) - Оказана психо-социальная поддержка 10 семьям, на попечение которых находятся10 молодых инвалидов. - Проведено 6 мастер классов по формированию профессиональных навыков и умений в области имиджа и стиля (длительность одного мастер класса 2 часа). - Проведено: 1 балл – маскарад «Зимняя сказка», 1 благотворительный концерт «Ноты милосердия». - Проведено 6 занятий: музыкально-ритмические, постановка подиумного шага, позиринг. - Развиты новые навыки и умения в сфере парикмахерского искусства (выполнения повседневных и вечерних причесок и укладок, нанесение дневного и вечернего макияжа, создание целостного образа). - Организованно 2 тематические фотосессии. - Привлечено в деятельность волонтерской группы 4 новые семьи, на содержании которых находятся молодые инвалиды, 5 волонтеров. - Проведено 2 круглых стола с целью налажено сотрудничества с организациями-партнерами. - Организовано участие целевой группы в конкурсе «Мир фантазии», «Здравствуй, Мир!» - Разработана новая коллекция причесок и костюмов для участников акции «Твори добро!». - Оборудовано три рабочих места для работы инвалидов. - Размещено 4 статьи в СМИ о реализации проекта.

3.4. Мероприятия Представьте список мероприятий, с указанием деталей и числа участников. Дата проведения; Название мероприятия; Количество участников; Место проведения. 1 месяц; Круглый стол по привлечение партнеров к реализации волонтерской инициативы; 25; Борисовская РО БОКК. 1 месяц; Вводный курс волонтера «Мы одна большая семья»; 20; Борисовская РО БОКК «Волонтерский клуб». 1 месяц; Музыкально-ритмические занятия; 15; ГУДО ЦТДиМ детская комната «УНИКУМ». 1 месяц; Занятие по парикмахерскому делу «Укладка холодным способом»; 16; ГУДО ЦТДиМ детская комната «УНИКУМ». 2 месяц; Музыкально-ритмические занятия; 15; ГУДО ЦТДиМ детская комната «УНИКУМ». 2 месяц; Занятие по фотопозирингу; 15; ГУДО ЦТДиМ детская комната «УНИКУМ». 2 месяц; Балл-маскарад «Зимняя сказка»; 30; Борисовский ТЦСОН. 2 месяц; Занятие по визажу «Нанесение дневного макияжа»; 16; ГУДО ЦТДиМ детская комната «УНИКУМ». 3 месяц; Занятие по фотопозирингу; 15; ГУДО ЦТДиМ детская комната «УНИКУМ». 3 месяц; Тематические фотосессии «Подари тепло души» (2); 15; Фотостудия 5Foto.by. 3 месяц; Занятие по парикмахерскому делу «Выполнение укладок горячим способом»; 16; ГУДО ЦТДиМ детская комната «УНИКУМ». 4 месяц; Создание коллекции «Твори добро!»; 30; ГУДО ЦТДиМ детская комната «УНИКУМ». 4 месяц; Подготовка образов моделей к конкурсу «Мир фантазии» (постановка подиумного шага); 30; ГУДО ЦТДиМ детская комната «УНИКУМ». 4 месяц; Занятие по визажу «Нанесение вечернего макияжа»; 16; ГУДО ЦТДиМ детская комната «УНИКУМ». 5 месяц; Участие в конкурсе «Мир фантазии»; 5; ГДК им. Горького. 5 месяц; Постановка подиумного шага; 16; ГУДО ЦТДиМ детская комната «УНИКУМ». 5 месяц; Занятие по парикмахерскому делу «Выполнение причесок с использование накладных элементов»; 16; ГУДО ЦТДиМ детская комната «УНИКУМ». 6 месяц; Выездная фотосессия «Цветы весны»; 15; Борисовский район. 6 месяц; Круглый стол по подведению итогов реализации инициативы; 15; Борисовская РО БОКК. 7 месяц– анализ результатов и подведение итогов проекта.

- Сроки осуществления проекта Укажите сроки начала и завершения проекта и даты проведения мероприятий. - Помните, что этот период должен включать в себя и подготовку, и время, необходимое для предоставления отчетности. 7 Месяцев

- Продолжение проекта после завершения финансовой поддержки со стороны донора - Важно показать, что проект не «умрет» с прекращением финансирования со стороны донора, что результаты будут иметь долгосрочный эффект и действительно окажут воздействие на жизнь целевой группы. Волонтёры, прошедшие подготовку, будут вовлекать в волонтёрское движение своих сверстников, проводить семинары, мастер-классы.

- Бюджет. Укажите размер расходов по каждому мероприятию и статье, а также общий итог. (количество участников 25 человек) Запрашиваемые ресурсы: 10 000эквивалент в долларах США Собственные ресурсы: 1000эквивалент в долларах США

- Партнеры Укажите, в сотрудничестве/при поддержке кого (предприятие, противотуберкулезное учреждение, Центр гигиены и общественного здоровья и т.д.) будет осуществляться проект. - Не забудьте приложить письма поддержки Государственное учреждение «Территориальный центр социального обслуживания населения Борисовского района»,Борисовская РО БОКК.

Будем рады сотрудничеству!

Humanitarian project of the state institution of additional education

«Center of creativity of children and youth of Borisov district»

The purpose of the project: Providing psychosocial support to 10 families  which takes care of 10 young people with disabilities

| а. | The name of the project : | «Impulse» |
| --- | --- | --- |
| b. | The name of primary organization / club / volunteer group applying: | The state institution of additional education «Center of creativity of children and youth of Borisov district» |
| с. | FULL NAME. The head of the organization / club / volunteer group: | Olga Ivanovna Verbitskaya |
| d. | Contact number: | +375298712080 |
| е. | The name of organization, institution, on the basis of which the project will be implemented: | The state institution of additional education «Center of creativity of children and youth of Borisov district» |
| f. | The place of implementation (address where the project will be implemented) | Minsk region, Borisov, Street March,8 d. 26. Children's room «UNICUM» |
| g. | FULL NAME. The head of the institution: | Galina Aleksandrovna Luzhkovskaya |
| h. | Phone number: | 8017(77)47072 |
| i. | Fax number: | 8-017(77) 51789 |
| j. | E-mail: | ddut@tut.by |
| k. | Mailing address: | 2222120 Minsk region, Borisov, Dzerzhinsky street, 42 |
| l. | Amount of requested financial support: | 10 000 in US dollars |

1. Who will implement the project? Indicate the number of volunteers, their age, place of work, theirposition. Indicate who is the leader of the volunteer group and has overall responsibility for project implementation and reporting. -Olga Ivanovna Verbitskaya– a project manager - 36 years old, the teacher of the state institution of additional education «Center of creativity of children and youth of Borisov district». -Volunteers at the age of 13-17 in the amount of 6 peoplewho are pupils of the interests association «Lady Perfection» of the state institution of additional education «Center of creativity of children and youth of Borisov district».

2. Target group of the project. Indicate which target group (age, number, type of employment) activities will be directed to. Ten families, in the care of which there are ten disabled people aged 18 to 35 years old with a violation of the musculoskeletal system. 3 disabled people live in single-parent families, 6 volunteers take part in the project.

3. The description of the humanitarian project: 3.1.The description of the problem / situation. 4817 pupils are enrolled in the state institution of additional education «Center of creativity of children and youth of Borisov district». Of these, 67 are disabled. Ten families who are taking care of 10 people with disabilities at the age of 18 to 35 years (CP) are ready to acquire professional skills in the beauty industry (hairdressing, clothing designer, clothing demonstrator) for further self-sufficiency and self - development.

3.2. The purposeof the project: Describe the goal of the project. The goal is to provide psycho-social support to families with carefor the disabled.

3.3. Project results Describe the final result of the planned activities, which can be seen and estimate (there may be several results) 1. Psycho-social support was provided to 10 families who are taking care of 10 people with disabilities. 2. 6 master classes were carried out for the formation of professional skills and abilities in the field of image and style (duration of one master class 2 hours). 3. Held: 1 costume ball «Winter's Tale», 1 charity concert «Notes of Mercy». 4. 6 classes were held: musical and rhythmic, setting a podium step, positioning. 5. Developed new skills and habits in the field of hairdressing (performing daily and evening hairstyles and hair styling, applying day and evening make-up, creating a complete image). 6. Organized 2 thematic photo shoots. 7. Invited to the activities of the volunteer group 4 new families, the content of which are young people with disabilities, 5 volunteers. 8. 2 round tables were held with the aim of establishing cooperation with partner-organizations. 9. Organized the participation of the task force in the competition "World of fantasy", «Hello, World!» 10. A new collection of hairstyles and costumes has been developed«Do good!». 11. Three workplaces for disabled people were equipped. 12. Posted 4 articles in the media aboutthe project implementation.

3.4. Activities Provide a list of events, with details and number of participants.

Date; The name of activities; Number of participants; Place of the activities. The first month; Round table on attracting partners to the implementation of volunteer initiatives; 25; The Belarusian Red Cross Society organization of Borisov district. The first month; The introductory volunteer course «We are one big family»; 20; The Belarusian Red Cross organization «Volunteer Club» of Borisov district. The first month; Musical and rhythmic classes; 15; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The first month; Hairdressing lesson «Cold hair styling »; 16; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The second month; Musical and rhythmic classes; 15; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The second month; Photo Possession Class; 15; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The second month; Costume ball «Winter*s Tale»; 30; The territorial center for social services of the population of Borisov district. The second month; Make-up lesson «Applying day make-up»; 16; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The third month; Photo Possession Class; 15; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The third month; Thematic photo shoots «Give the warmth of the soul»(2); 15; Photo Studio 5Foto.by. The third month; Hairdressing lesson «Performing hair styling in a hot way»; 16; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The fourth month; Creating a collection of «Do good!»; 30; The children'sroom «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The fourth month; Preparation of images of models for the competition «World of fantasy» (setting the podium step); 30; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The fourth month; Make-up lesson «Applying an evening make-up»; 16; The children's room «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The fifth month; Participation in the competition «World of fantasy»; 5; The Gorky Culture Palace. The fifth month; Setting the podium step; 16; The children'sroom «UNICUM» of the state institution «Center of creativity of children and youth of Borisov dictrict». The fifth month; Hairdressing lesson «Making hairstyles with the use of overhead elements»; 16; The children's room «UNICUM» of the stateinstitution«Center of creativity of children and youth of Borisov dictrict». The sixth month; Visiting photo shoot «Flowers of Spring»; 15; Borisov district. The sixth month; Roundtable on summing up the implementation of the initiative; 15; The Belarusian Red Cross Society organization of Borisov district. The seventhmonth–analysis of the results and summarizing the project.

4.Project duration: Terms of starting and finishing the project. - Remember that this period should include both preparation and the time required for reporting. - 7 months

5. Continuation of the project after completion offinancial support from the donor - It is important to show that the project will not "die" with the cessation of funding from the donor, that the results will have a long-term effect and will indeed have an impact on the life of the target group. Trained volunteers will involve their peers in the volunteer movement, conduct seminars, workshops.

6.Budget Indicate the amount of expenses for each event and article, as well as the total. (number of participants 25 people) Resources requested: 10,000 in US dollars Own resources: 1000 in US dollars

7. Partners Indicate, in collaboration / with the support of whom (the enterprise, the tuberculosis institution, the Center for hygiene and public health, etc.) the project will be implemented. Do not forget to attach letters of support The state institution «The territorial center for social services of the population of Borisov district», the Belarusian Red Cross Society organization in Borisov region.

We will be glad tocooperate!