Гуманитарный проект ГУДО «Центр творчества детей и молодежи Борисовского района».

Цель проекта: Создание инклюзивной среды

- Наименование проекта: «Мир без границ»

- Срок реализации проекта: 15 месяцев

- Организация - заявитель, предлагающая проект:

- Цель проекта: создание инклюзивной среды на базе туристического комплекса ГУДО «Центр творчества детей и молодёжи Борисовского района» в деревне Кричино для организации отдыха детей и молодёжи с инвалидностью.

- Задачи, планируемые к выполнению в рамках реализации проекта:

- разработка проекта инклюзивной среды на базе Кричино,

- перепланировка комнат,

- сооружение зеленого класса,

- установка воркаут площадок,

- оборудование веревочного парка в кронах деревьев,

- организация бивачной зоны,

- организация безбарьерной среды,

- подготовка волонтеров для работы с детьми с особенностями,

- разработка образовательных модулей инклюзивной среды,

- приобретение транспорта для перевозки инвалидов колясочников.

- Целевая группа: подростки с различной степенью инвалидности, волонтеры, дети нуждающиеся в рекреации.

- Краткое описание мероприятий в рамках проекта:

Перепланировка и ремонт здания, благоустройство территории базы Кричино.

| 8. Общий объем финансирования (в долларах | США): 238.000 |
| --- | --- |
| Источник финансирования | Объем финансирования (в долларах США) |
| Средства донора | 230 000 |
| Софинансирование | 8 000 |
| 9. Место реализации проекта (область/район, город): Минская область, г.Борисов, ул. Дзержинского, 42; тел. |  |
| 10. Контактное лицо: Мороз Сергей Васильевич +375291641102, факс – 8(0177) 94 28 77; е-mail: ddut@tut.by |  |

Кратное описание гуманитарного проекта: в г. Борисове и Борисовском районе проживают 578 семей, в которых воспитывается 591 ребёнок с инвалидностью до 18 лет. У семей, воспитывающих детей с разной степенью инвалидности возникают проблемы организовать отдых детей в каникулярное время на природе в компании сверстников.

Ожидаемые результаты:

Создана инклюзивная среда на базе Кричино для детей с инвалидностью, соответствующая их особым образовательным потребностям, открытая для их родителей (законных представителей), гарантирующая сохранение и укрепление физического и психологического здоровья.

Будем рады сотрудничеству!

Humanitarian project of the state institution of additional education  «Center of creativity of children and youth of Borisov district».

The purpose of the project:  the creation of the inclusive environment.

- The name of the project: «The world without borders»

- Project duration: 15 months

- The applicant organization proposing the project: The state institution of additional education  «Center of creativity of children and youth of Borisov district»

- The  purpose of the project: the creation of the inclusive environment based on the tourist complex of the state institution of additional  education "Center of creativity of  children and youth of  Borisov District" in the village of  Krichino to organize the recreation of  children and young people with disabilities.

- The objectives  planned to be performed within the project implementation:

-  the development of  the inclusive environment project ,

- the  reconfiguration of rooms,

- the construction of the  green classrom,

- the installation of workout sites,

- the fitment of the  rope park in the trees crowns ,

- the organization of the bivouac zone,

- the establishment of a barrier-free environment ,

- the development of educational modules of the inclusive environment project,

- the purchase of vehicles for the transport of disabled wheelchairs users.

- Target group: adolescents with varying degrees of disability, volunteers, children in need of recreation.

- The brief description of the project activities: The reconfiguration  and renovation of the building, the  improvement of the territory of the  base of Krichino.

| 8. Total amount of financing (in US dollars) | : 238.000 |
| --- | --- |
| Source of financing | Amount of financing (in US dollars) |
| Donor funds | 230 000 |
| Co-financing | 8 000 |
| 9. Place of the project implementation (region/district, city): Minsk region, Borisov, Dzerzhinsky street 42 ,phone 80177747074 |  |
| 10. Contact person : Sergey Vasilyevich Moroz +375297038238, fax – 8(0177) 94 28 77; е-mail: ddut@tut.by |  |

The brief description of the humanitarian project: In the town of Borisov and in  Borisov district live 578 families in which 591 children with disabilities under 18 are raised. Families raising children with different degrees of disabilities  have problems in organising childrens recreation in nature during the holidays in the company of their peers.

Expected results: An inclusive environment on the basis of  Krichino for children with disabilities has been created corresponding to their special educational needs. It is open to their parents (their legal representatives) guaranteeing the preservation and promotion  of their  physical and psychological health.

We will be glad to cooperate!